## Timelines
| Maconomy ID | 10018137-1
| Confluence | https://btsdigital.atlassian.net/wiki/spaces/DP/pages/5995069441/Allegis+2026+Shareholder+Meeting+Customization+Pulse+MBS
| Process Step | Stakeholder | Start Date | End Date | Comments (if any)
1 | Receive inputs | Kevin | 2026-10-07
2 | Development | Developer | 2026-10-08 | 2026-10-09 | 1/2 day each
3 | Styling | Designer | 2026-10-09 | 2026-10-09
4 | Pre-dev review | Kevin / Smita | 2026-10-12 | 2026-10-12
5 | Incorporate review comments | Developer/Designer | 2026-10-13 | 2026-10-13 | Developer: 4 hr Designer: 2 hr
6 | Review Solution - R1 | Kevin | 2026-10-14 | 2026-10-14
7 | Incorporate review comments | Developer/Designer | 2026-10-15 | 2026-10-15 | Developer: 2 hr Designer: 1 hr
8 | Review Solution - R2 | Kevin | 2026-10-16 | 2026-10-16
9 | Incorporate review comments | Developer/Designer | 2026-10-19 | 2026-10-19 | Developer: 2 hr Designer: 1 hr

## Estimates
Developer | Designer
Based on the shared requirements, I estimate that 8 hours, including both development and testing, should be sufficient. | Tasks | Time
| Briefing + Branding study | 0.5 day
Self-review and Device run-through - Laptop up to 125% zoom + iPad
Peer review + comments implementation
| Images - search, edit and insert | 0.5 day
Main UI - Top band, Background, Fonts, Colors, common header
Welcome Screen, Team name entry page
Tabs, Case study
GD / Fac / Rep / leader/ followers/ heatmap
single select, feedback & Results, Brainstorm & Result, Ranking, Leaderboard